## OUR JOURNEY TO NET ZERO
[9 empty] | TOTAL INITIATIVES | [14 empty] | X*
TOTAL INITIATIVES UPDATED
#Actions 2023
|  | #Actions 2024 | [19 empty] | #Actions Owner
|  | #Actions 2025 | [19 empty] | #Actions Stakeholder
Our ambition |  | Accelerate decarbonisation across our ecosystem
| Source | Recurrency (Y/N) | Start Year | End Year | ID | Initiative | Transversal (T) vs Specific (S) | Incremental (I) vs Additional (A) | KPI | Target | Target 2023 |  |  |  | Target 2024 |  |  |  | Target 2025 |  |  |  | Commercial | Renewables | New Businesses | P&O Upstream | P&O Refinery | P&O ROL | Energy Management | CC HSE | CC People | CC Risk | CC Compliance & Legal | CC CSI & Comms | CC Procurement | CC P&P | CC IR | CC IT | CC Facilities | CC External Relations | Internal Audit | CC Finance | Data Office | Innovation | Account & Tax | S&S | Co-owner?
Driver #1 |  | Clear and effective oversight and management of climate | [8 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| S&S | Y | 2023 |  | F1_001 | Align long term scenarios to be used in climate risk assessment; Evaluate the alignment of the company's long term strategy with the Paris Agreement and WB2C and 1.5ºC scenarios and Assess the resilience of the strategy, taking into account different climate scenarios (qualitatively relating to previously disclosed transition risks and opportunities) | T | I | Evaluation performed | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [23 empty] | O - Cláudia Santiago |  | 1
| S&S, Upstream, Refinery, RM | Y | 2023 |  | F1_002 | Access climate risks and opportunities assessment in an annual basis (physical and transition risks) and develop action plans and mitgation measures according to the expected loss and CVaR (Climate Value at Risk) | T | I | nºassessments/year | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | S | S |  | S | S | S |  |  |  | S - Ana Sofia Silva | [13 empty] | O - Cláudia Santiago |  | 2
| S&S | N | 2023 |  | F1_003 | Develop an internal standard for climate risks and opportunities assessment, including its process and methodology | T | A | nº Capacity Building session about new standard | 1 | 0 | 0 | 0 | 1 | - | - | - | - | - | - | - | - | [9 empty] | S - Ana Sofia Silva | [13 empty] | O - Cláudia Santiago |  | 1
| S&S | Y | - |  | F1_004 | Bring outside-in view to Excom/Board/Sustainability Committee with externals on climate related issues (e.g risk assessment; TCFD alignment) | T | I | [37 empty] | O - Cláudia Santiago |  | 3
| S&S | Y | - |  | F1_005 | Quarterly report to the BoD and CEO the CO2 performance against targets, decarbonization roadmap status update or any key climate change related issues | T | I | nº reports performed/year | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | [23 empty] | O - Cláudia Santiago |  | 4
Driver #2 |  | Reduce and mitigate our GHG emissions | [8 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| S&S | Y | 2023 |  | F1_009 | Define relevant interim targets (short/ medium/long; scope 1 + 2) | T | A | Targets defined | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [23 empty] | O- Cláudia Santiago |  | 8
| S&S | Y | 2023 |  | F1_010 | Define absolute scope 3 targets (short/ medium/long) | T | A | Targets defined | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [23 empty] | O- Cláudia Santiago |  | 9
| S&S | Y | 2023 |  | F1_011 | Define dedicated methane targets | T | A | Targets defined | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [23 empty] | O- Cláudia Santiago |  | 10
| S&S | N | 2023 |  | F1_012 | Subscribe to OGCI's "Aiming for Zero Methane Emissions Initiative" | S | A | Subscrition | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [23 empty] | O- Cláudia Santiago |  | 11
| S&S, COM | N | 2023 |  | F1_013 | Certify a carbon tool to quantify the GHG emissions of sold products to customers | T | A | Certification | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | S - Joana Duarte | [22 empty] | O- Cláudia Santiago |  | 2
| S&S, EM | N | 2023 |  | F1_014 | Calculate EM carbon Footprint and define targets to mitigate it | S | A | % EM carbon footprint calculated | 100% | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [6 empty] | S - Sara Montenegro | [16 empty] | O- Cláudia Santiago |  | 3
Our ambition |  | Reshape our portfolio with focus on low carbon |  |  |  | This ambition will not be monitored under the scope of the sustainability roadmap

## PRESERVE AND RESTORE OUR PLANET
[10 empty] | TOTAL INITIAL INITIATIVES |  |  |  | TOTAL INITIAL INITIATIVES | [10 empty] | x*
[10 empty] | TOTAL INITIATIVES UPDATED |  |  |  | TOTAL INITIATIVES UPDATED
#Actions 2023
|  | #Actions 2024 | [20 empty] | #Actions Owner
|  | #Actions 2025 | [20 empty] | #Actions Stakeholder
Our ambition |  | Net positive impact on biodiversity
| Source | Recurrency (Y/N) | Start Year | End Year | ID old | ID | Initiative | Transversal (T) vs Specific (S) | Incremental (I) vs Additional (A) | KPI | Target | Target 2023 |  |  |  | Target 2024 |  |  |  | Target 2025 |  |  |  | Commercial | Renewables | New Businesses | P&O Upstream | P&O Refinery | P&O ROL | Energy Management | CC HSE | CC People | CC Risk | CC Compliance & Legal | CC CSI & Comms | CC Procurement | CC P&P | CC IR | CC IT | CC Facilities | CC External Relations | Internal Audit | CC Finance | Data Office | Innovation | Account & Tax | S&S | Co-owner?
Driver #1 |  | Commit to include biodiversity related criteria in the decision-making | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| Upstream | N | 2023 | - | 66 | F2_001 | Use IBAT or similar tool to evaluate the presence of sensitive areas within locations of operated sites (according with GALP's Standards) | T | I | % Galp sites covered | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | O - HSE | O - HSE | O - HSE | O - HSE | O - HSE | O - HSE |  | S - Margarida Magina | [7 empty] | S - IT
| S&S | Y | - | - | 67 | F2_002 | Assess Biodiversity Risks in an annual basis | T | I | nº assessments/year | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | S - HSE | S - HSE | S - HSE | S - HSE | S - HSE | S - HSE | [17 empty] | O - Cláudia Santiago
| HSE CC | N | 2023 | 2023 | 68 | F2_003 | Update GALP's Standards to include biodiversity and water risk assessment tools /methods as a key factor to support decision about future projects, including KPIs (Update NT-R-008) | T | A | nº Capacity Building session about new standard | 1 | 0 | 0 | 0 | 1 | - | - | - | - | - | - | - | - | S - HSE | S - HSE | S - HSE | S - HSE | S - HSE | S - HSE |  | O - Margarida Magina | [15 empty] | S - Cláudia Santiago
| HSE CC | Y | 2023 | - | 69 | F2_004 | Define KPIs and targets for biodiversity - BUs | T | A | KPIs defined | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | S - HSE | S - HSE | S - HSE | S - HSE | S - HSE | S - HSE |  | O - Margarida Magina | [15 empty] | S - Cláudia Santiago
Driver #2 |  | Embed our sites in the ecosystem | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| HSE CC | N | 2023 | 2023 | 71, 80 | F2_005 | Update Galp's Standards to include biodiversity actions plans/NPI approach and other efficiency plans in the whole life cycle of the projects (Update NT-R-008) | T | A | n.º Capacity Building session about news standards | 1 | 0 | 0 | 0 | 1 | - | - | - | - | - | - | - | - | S-HSE | S-HSE | S-HSE | S-HSE | S-HSE | S-HSE |  | O - Margarida Magina | [15 empty] | S - Cláudia Santiago
| HSE CC | N | 2023 | 2023 | 72 | F2_006 | Create a Galp Biodiversity Policy/Galp Biodiversity Position (transversal and for existing and new proj) | T | A | Policy released | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | S-HSE | S-HSE | S-HSE | S-HSE | S-HSE | S-HSE |  | S - Margarida Magina | [15 empty] | O - Cláudia Santiago
| RNW |  | 2023 |  | 74,75,76, 82 | F2_007 | Implement a pilot project NPI approach in new operated projects in or adjacent to sensitive areas | S | A | % implementation according with action plan | >90% | 0 | >90% | >90% | >90% | >90% | >90% | >90% | >90% | >90% | >90% | >90% | >90% |  | O - António Fonseca | [5 empty] | S - Margarida Magina | [15 empty] | I - Cláudia Santiago
| Refinery, ROL, COM, RNW | N | 2024 |  | 73.305 | F2_009 | Define and Implement a Biodiversity Action Plan for existing sites located in sensitive areas | T | A | BAP in existing sites located in sensitive areas/total existing sites located in sensitive areas (%) | 100% | - | - | - | - | 0% BAP defined | <25% BAP defined | <50% BAP defined | <75% BAP defined | 100% BAP defined | 0% BAP implemented | <75% BAP implemented | 100% BAP implemented | O - HSE | O - HSE | O - HSE | O - HSE | O - HSE | O - HSE |  | S - Margarida Magina | [15 empty] | I - Cláudia Santiago
Driver #3 |  | Collaborate through initiatives and partnerships | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| S&S | N | 2023 | 2023 | 87 | F2_012 | Sign act4nature | S | A | Protocol Signed | Y | 0 | 0 | Y | Y | - | - | - | - | - | - | - | - | [23 empty] | O - Cláudia Santiago
| S&S | N | 2023 | 2025 | 88, 89, 90 | F2_013 | Develop, implement and public disclose TNFD Framework | S | A | %performed action plan | >90% | - | - | 100% Action plan defined, identifying milestone per Q | >90% | >90% | >90% | >90% | >90% | >90% | >90% | >90% | Public disclose | [23 empty] | O - Cláudia Santiago
Our ambition |  | Effective Water Stewardship
|  | Recurrency (Y/N) | Start Year | End Year | ID |  | Initiative | Transversal (T) vs Specific (S) | Incremental (I) vs Additional (A) | KPI | Target | 1Q: Target 2023; 1Q: Target 2024; 1Q: Target 2025 | Commercial | Renewables | New Businesses | P&O Upstream | P&O Refinery | P&O ROL | Energy Management | CC HSE | CC People | CC Risk | CC Compliance & Legal | CC CSI & Comms | CC Procurement | CC P&P | CC IR | CC IT | CC Facilities | CC External Relations | Internal Audit | CC Finance | Data Office | Innovation | Account & Tax | S&S
Driver #1 |  | Understand and conserve water resources | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| S&S | Y | - | - | 91 | F2_014 | Assess Water Risks in an annual basis | T | I | nº assessments/year | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | S - HSE | S - HSE | S - HSE | S - HSE | S - HSE | S - HSE | [17 empty] | O - Cláudia Santiago
| Upstream | N | 2023 | - | 92 | F2_015 | Use Water Risk tool (WRI) or similar tool to evaluate our presence in water stress areas | T | I | % Galp sites covered | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | O - HSE | O - HSE | O - HSE | O - HSE | O - HSE | O - HSE |  | S - Margarida Magina
| HSE CC | N | 2023 | 2023 | 94 | F2_016 | Update GALP's Standards to include Water Risk assessment tools /methods as a key factor to support decision about future projects, including KPIs | T | A | n.º Capacity Building session about new standard | 1 | 0 | 0 | 0 | 1 | - | - | - | - | - | - | - | - | [7 empty] | O - Margarida Magina | [15 empty] | S - Cláudia Santiago
| HSE CC | Y | 2023 | - | 95 | F2_017 | Define KPIs and targets for water - BUs | T | A | KPIs and targets defined | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [7 empty] | O - Margarida Magina | [15 empty] | S - Cláudia Santiago
| NEW | Y | 2023 | - | 344 | F2_038 | Define KPIs and targets for water - overall Galp | T | A | KPIs and targets defined | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [7 empty] | S - Margarida Magina | [15 empty] | O - Cláudia Santiago
| Refinery | N | 2025 |  | 102 | F2_018 | Treat and reuse water effluents from Sines refinery or from Sines Industrial Area | S | A | % action implemented | - | - | - | - | - | - | - | - | - | - | - | - | 100% |  |  |  |  | O - Bruno Santos/Maria António |  |  | S - Margarida Magina | [15 empty] | S - Claudia Santiago
Our ambition |  | Operational excellence and transition towards circularity
|  | Recurrency (Y/N) | Start Year | End Year | ID |  | Initiative | Transversal (T) vs Specific (S) | Incremental (I) vs Additional (A) | KPI | Target | Target 2023 1Q: Target 2023; Target 2024 1Q: Target 2024; Target 2025 1Q: Target 2025 | Commercial | Renewables | New Businesses | P&O Upstream | P&O Refinery | P&O ROL | Energy Management | CC HSE | CC People | CC Risk | CC Compliance & Legal | CC CSI & Comms | CC Procurement | CC P&P | CC IR | CC IT | CC Facilities | CC External Relations | Internal Audit | CC Finance | Data Office | Innovation | Account & Tax | S&S
Driver #1 |  | Optimise resources, effluents, emissions and waste | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| HSE CC | N | 2023 | 2023 | 112, 93 | F2_024 | Review HSE Policy - highlight operational efficiency (circular economy) + water | T | A | Policy updated released | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [7 empty] | S - Margarida Magina | [15 empty] | O - Cláudia Santiago
| HSE CC | Y | 2023 | - | 113, 114,115,116,117 | F2_025 | Define KPIs and targets for eco efficiency-related - BUs | T | I | KPIs and targets defined | Y | 0 | 0 | 0 | Y | 0 | 0 | 0 | Y | 0 | 0 | 0 | Y | S | [6 empty] | O - Margarida Magina | [15 empty] | S - Cláudia Santiago
| NEW | Y | 2023 | - | 343 | F2_039 | Define KPIs and targets for eco efficiency-related - overall Galp | T | I | KPIs and targets defined | Y | 0 | 0 | 0 | Y | 0 | 0 | 0 | Y | 0 | 0 | 0 | Y | S | [6 empty] | S - Margarida Magina | [15 empty] | O - Cláudia Santiago
| Refinery | N | 2023 |  | 118 | F2_026 | Use FCC Catalyst to St. Gobain to produce bitumen (circular economy) | S | A | % action implemented | 100% | 100% | 100% | 100% | 100% | - | - | - | - | - | - | - | - |  |  |  |  | O - Bruno Santos/Maria António |  |  | S - Margarida Magina
| Refinery, COM, RNW, ROL, Upstream | N | 2023 |  | 120,121,126, 128, 129, 135, 136,101 | F2_027 | Define and endorse an operational ecoefficiency action plan | S | I | ecoeficiency action plan defined in priority sites/total priority sites (%) | 100% | 0 | 0 | 0 | 100% | - | - | - | - | - | - | - | - | O - HSE | O - António Fonseca |  | O | O - Bruno Santos/Maria António | O - Silvia Romeiro |  | S - Margarida Magina | [15 empty] | I - Cláudia Santiago
| NEW | N | 2024 |  | 341 | F2_028 | Implement an operational ecoefficiency action plan | T | I | % ecoefficiency KPIs achived in priority sites | 100% | - | - | - | - | 0 | 0 | 0 | >90% | 0 | 0 | 0 | >90% | O | O |  | O | O | O |  | S - Margarida Magina
| Facilities | N | 2023 | 2024 | 123, 124, 125 | F2_029 | Implement HESTIA plan in the new HQ (F2): - LEED platinum indoor water use reduction requirement on new headquarters - Define waste and water management strategies and initiatives for new headquarters (e.g. zero reusable platic) - Promote the reuse of furniture through donations | S | A | nº actions started implemented | X | 0 | 0 | 0 | 3 | - | - | - | - | - | - | - | - | [7 empty] | S - Margarida Magina | [8 empty] | O - Nelson Lucas Rosa | [6 empty] | S - Cláudia Santiago
| Refinery, Facilities |  | 2024 |  | 119.133 | F2_030 | Reuse leftover food - Refinery Canteen and new HQ | S | A | % action implemented | - | - | - | - | - | - | - | - | 100% | 100% | 100% | 100% | 100% |  |  |  |  | O |  |  | S - Margarida Magina | [8 empty] | O

## BOOST A JUST TRANSITION FOR ALL
[10 empty] | TOTAL INITIATIVES | [14 empty] | X*
TOTAL INITIATIVES UPDATED
#Actions 2023
|  | #Actions 2024 | [20 empty] | #Actions Owner
|  | #Actions 2025 | [20 empty] | #Actions Stakeholder
Our ambition |  | People-centric energy transition
| Source | Recurrency (Y/N) | Start Year | End Year | ID old | ID | Initiative | Transversal (T) vs Specific (S) | Incremental (I) vs Additional (A) | KPI | Target | Target 2023 |  |  |  | Target 2024 |  |  |  | Target 2025 |  |  |  | Commercial | Renewables | New Businesses | P&O Upstream | P&O Refinery | P&O ROL | Energy Management | CC HSE | CC People | CC Risk | CC Compliance & Legal | CC CSI & Comms | CC Procurement | CC P&P | CC IR | CC IT | CC Facilities | CC External Relations | Internal Audit | CC Finance | Data Office | Innovation | Account & Tax | S&S | Co-onwer?
Driver #1 |  | Encourage social dialogue and stakeholder engagement | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| S&S | N | 2023 |  | 137,144,145 | F3_001 | Define a just transition plan: - Identify and assess the social risks and impact of the energy transition on employees, affected communities and its business relationships -Define action plan to mitigate the social impacts of the just transition on employees, affected communities and its business relationships | T | A | Just Transition Plan defined | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [23 empty] | O - Cláudia Santiago
| S&S | N | 2023 |  | 138 | F3_002 | Develop a double materiality assessment | T | A | Materiality assessment published | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [23 empty] | O - Cláudia Santiago
Driver #2 |  | Skill all employees for the challenges of the energy transition | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| S&S, COM |  | 2023 |  | 153 | F3_009 | Train the customer facing employees (call center; service stations; etc) with the right skills to face the new challenges of the energy transition |  |  | nº training sessions performed/nºtraining sessions planned | 100% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | O | [7 empty] | O - Marco Serrão | [14 empty] | S - Cláudia Santiago
Driver #3 |  | Empower communities through social investment | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| CSI&Comms |  | 2023 |  | 143 | F3_010 | Create the guidelines and requirements for Community Engagement Plans of each project/community | T |  | N# Community Engagement Plans | % Galp communities covered | [23 empty] | O - Sandra Aparicio
| CSI&Comms |  | 2023 |  | 156 | F3_011 | Define the Community Engagement and Social Acceptance priorities areas of investment and support |  |  | % execution | 100% | [23 empty] | O- Sandra Aparício | [9 empty] | S
| CSI&Comms |  | 2023 |  | 157 | F3_012 | Define and implement a Community Engagement Plan for the geographies where we operate/have projects on |  |  | N# initiatives; € invested | % Galp communities covered | [12 empty] | O | O | O | O | O | O | [5 empty] | S- Sandra Aparício
| CSI&Comms |  | 2023 |  | 158 | F3_013 | Define the Communication Plan for the community engagement initiatives |  |  | N# communications | % Galp communities covered | [12 empty] | O | O | O | O | O | O | [5 empty] | S- Sandra Aparício
| CSI&Comms |  | 2023 |  | 159 | F3_014 | Define the KPIs for Community Engagement, in accordance with the ESG frameworks followed by Galp |  |  | N# goals accomplished | % Galp communities covered | [12 empty] | O | O | O | O | O | O | [5 empty] | S- Sandra Aparício
| CSI&Comms |  | 2023 |  | 160 | F3_015 | Define a strategic sponsorship program focused on energy topics (Future Up; Ciência Viva) |  |  | N# initiatives; N# schools | % Communities covered | [23 empty] | O - Sandra Aparício | [9 empty] | S
Our ambition |  | Promote Diversity, Equity & Inclusion (DE&I) everyday
|  | Recurrency (Y/N) | Start Year | End Year | ID |  | Initiative | Transversal (T) vs Specific (S) | Incremental (I) vs Additional (A) | KPI | Target | 1Q: Target 2023; 1Q: Target 2024; 1Q: Target 2025 | Commercial | Renewables | New Businesses | P&O Upstream | P&O Refinery | P&O ROL | Energy Management | CC HSE | CC People | CC Risk | CC Compliance & Legal | CC CSI & Comms | CC Procurement | CC P&P | CC IR | CC IT | CC Facilities | CC External Relations | Internal Audit | CC Finance | Data Office | Innovation | Account & Tax | S&S
Driver #1 |  | Elevate a DE&I culture and tackle inequalities | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| People, S&S |  | 2024 |  | 172 | F3_019 | Develop a risk management framework to reduce inequality, including the definition of metrics and targets |  |  | Risk management framework defined and started to be implemented | Y | - | - | - | - | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | [8 empty] | O - Marco Serrão | S - Ana Sofia Silva | [13 empty] | S - Cláudia Santiago
| NEW - emails and others |  | 2024 |  | 177 | F3_021 | Evaluate advertising & marketing content for gender bias |  |  | nº evaluations performed | 1 | - | - | - | - | 0 | 0 | 0 | 1 | - | - | - | - | O
Our ambition |  | Respect, protect and fulfil Human Rights
|  | Recurrency (Y/N) | Start Year | End Year | ID |  | Initiative | Transversal (T) vs Specific (S) | Incremental (I) vs Additional (A) | KPI | Target | Target 2023 1Q: Target 2023; Target 2024 1Q: Target 2024; Target 2025 1Q: Target 2025 | Commercial | Renewables | New Businesses | P&O Upstream | P&O Refinery | P&O ROL | Energy Management | CC HSE | CC People | CC Risk | CC Compliance & Legal | CC CSI & Comms | CC Procurement | CC P&P | CC IR | CC IT | CC Facilities | CC External Relations | Internal Audit | CC Finance | Data Office | Innovation | Account & Tax | S&S
Driver #1 |  | Address all findings and potential impacts | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
Driver #2 |  | Spread Human Rights awareness in our ecosystem | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| Procurement |  | 2024 |  | 180 | F3_026 | Develop a training plan/academia on HR for our suppliers |  |  | nºtrainings performed/nºtrainings planed - applied to suppliers with high HR risk | 100% | - | - | - | - | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | [8 empty] | S - Marco Serrão |  |  |  | O - Procurement
| Procurement |  | 2024 |  | 181 | F3_027 | Implement awareness initiatives involving 100% of suppliers with high human rights risk |  |  | nºawareness initiatives/year | 1 | - | - | - | - | 0 | 0 | 0 | 1 | [12 empty] | S - Marco Serrão |  |  |  | O - Procurement

## PROTECT AND EMPOWER OUR PEOPLE
[10 empty] | TOTAL INITIATIVES | [14 empty] | X*
TOTAL INITIATIVES UPDATED
#Actions 2023
|  | #Actions 2024 | [20 empty] | #Actions Owner
|  | #Actions 2025 | [20 empty] | #Actions Stakeholder
Our ambition |  | Safest energy company in the world
| Source | Recurrency (Y/N) | Start Year | End Year | ID old | ID | Initiative | Transversal (T) vs Specific (S) | Incremental (I) vs Additional (A) | KPI | Target | Target 2023 |  |  |  | Target 2024 |  |  |  | Target 2025 |  |  |  | Commercial | Renewables | New Businesses | P&O Upstream | P&O Refinery | P&O ROL | Energy Management | CC HSE | CC People | CC Risk | CC Compliance & Legal | CC CSI & Comms | CC Procurement | CC P&P | CC IR | CC IT | CC Facilities | CC External Relations | Internal Audit | CC Finance | Data Office | Innovation | Account & Tax | S&S | Co-onwer?
Driver #1 |  | Guarantee no personal harm for all | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| RM |  | 2023 |  | 186 | F4_001 | Ensure, through the definition and implementation of a contingency plan, the physical safety of our people in the event of demonstrations and instructions from activists | T |  | nº contigency plan released/nº critical sites | 100% | 0 | 0 | 0 | 100% | - | - | - | - | - | - | - | - |  |  |  |  | S - HSE |  |  |  |  | O - Ana Sofia Silva
| RM |  | 2023 |  | 187 | F4_002 | Perfom a security reassessment to Sines Logistic and Industrial Hub |  |  | Security reassessment performed | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - |  |  |  |  | S - HSE | S - Silvia Romeiro |  | O - Dough |  | S - Ana Sofia Silva
| HSE CC, Upstream |  | 2023 |  | 189, 182, 331 | F4_004 | Introduce a learning process based on the main conclusions of incidents or other safety relevant events | T | A | nº Safety Alert communications/nº total SIF-F | > 1/SIF-F | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | S | S |  | S | S | S |  | O - Filipa Gubert O - José Almeida
| HSE CC |  | 2023 |  | 190 | F4_005 | Review the recognition and deviations management standard on safety | T | A | nº Capacity Building session about updated standard | 1 | 0 | 0 | 0 | 1 | - | - | - | - | - | - | - | - | [7 empty] | O - Nuno Maia
| HSE CC |  | 2023 |  | 191 | F4_006 | Develop a Turnaround Revision Standard | S | A | nº Capacity Building session about created standard | 1 | 0 | 0 | 0 | 1 | - | - | - | - | - | - | - | - |  |  |  |  | S - Bruno F. Santos |  |  | O - José Almeida
Driver #2 |  | Prevent major industrial accidents | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| RM |  | 2023 |  | 200 | F4_012 | Perform industrial operational surveys in all critical assets ensuring the implementation of mitigation plans | S |  | nº industrial operational surveys performed/nº critical assets | 100% | 0 | 0 | 0 | 100% | - | - | - | - | - | - | - | - | [9 empty] | O - Ana Sofia Silva
| HSE CC |  | 2023 |  | 201 | F4_013 | Create Process Safety Fundamentals (PSF) for GALP |  |  | nº Capacity Building session about PSF created | 1 | 0 | 0 | 0 | 1 | - | - | - | - | - | - | - | - | [7 empty] | O - José Almeida
| HSE CC |  | 2023 |  | 203 | F4_015 | Develop AIPSM standard |  |  | nº Capacity Building session about Standard created | 1 | 1Q: 0; 2Q: 0; 3Q: 0; 4Q: 1 | [7 empty] | O - Márcio Muniz
Driver #3 |  | Incorporate safety culture in our DNA | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| ROL |  |  |  | 205 | F4_017 | Implement Road Transportation system | S |  | nº Capacity Building session about Standard created | 1 | [17 empty] | O - Vitor Piteira |  | S - Doug
| Facilities |  | 2023 |  | 206 | F4_018 | Develop a safety e-learning welcome training to the new offices | T | A | % applied workers trained | 100% | - | - | - | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | S - Doug | S - Marco Serrão | [7 empty] | O - André Miranda da Silva
| HSE CC |  | 2023 |  | 207 | F4_019 | Improve level of safe behaviors | T | I | nº safe behaviors/nº unsafe and safe behaviors | ≥80% | 0 | 0 | 0 | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% |  | S - António Fonseca | [5 empty] | O - José Almeida
| HSE CC |  | 2023 |  | 208 | F4_020 | Create a Safety Champions network | T | A | n.º of Trainned champions/nº of champions | 100% | 0 | 0 | 0 | 100% | - | - | - | - | - | - | - | - | S | S |  | S | S | S |  | O - Nuno Maia
| HSE CC |  | 2023 |  | 209 | F4_021 | Prepare and conduct an annual Safety Day in all geographies | T | I | nº events/year | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | S | S |  | S | S | S |  | O - Doug
| HSE CC |  | 2023 |  | 210 | F4_022 | Recognize best safety performers, including contractors, etc | T | I | Recognition event/year | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | S | S |  | S | S | S |  | O - Doug
| RNW |  | 2023 |  | 330 | F4_023 | Guarantee implementation of Safety talks in place with objectives and monitoring across all BUs |  |  | nº Safety Talks | X | [19 empty] | O
Our ambition |  | Galp as the greatest place to work
|  | Recurrency | Start Year | End Year | ID |  | Initiative | Transversal (T) vs Specific (S) | Incremental (I) vs Additional (A) | KPI | Target | 1Q: Target 2023; 1Q: Target 2024; 1Q: Target 2025 | Commercial | Renewables | New Businesses | P&O Upstream | P&O Refinery | P&O ROL | Energy Management | CC HSE | CC People | CC Risk | CC Compliance & Legal | CC CSI & Comms | CC Procurement | CC P&P | CC IR | CC IT | CC Facilities | CC External Relations | Internal Audit | CC Finance | Data Office | Innovation | Account & Tax | S&S
Driver #1 |  | Reenergise our people | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| Upstream |  | 2023 |  | 214 | F4_029 | Implement GROW Program | T |  | % Program implemented | 100% | 100% | 100% | 100% | 100% | - | - | - | - | - | - | - | - | [8 empty] | O - Marco Serrão
| EM |  | 2023 |  | 215 | F4_030 | Achieve a higher Engagement result (vs. Benchmark for Energy Industry) in the People Survey |  |  | Engagement level | 75%
| People |  | 2023 |  | 221 | F4_031 | Implement ENDORSE Referral Program | T |  | % Program implemented | 100% | 100% | 100% | 100% | 100% | - | - | - | - | - | - | - | - | [8 empty] | O - Marco Serrão
| NEW |  |  |  | 225 | F4_032 | Implement PLUS Program | T |  | % Program implemented | 100% | 100% | 100% | 100% | 100% | - | - | - | - | - | - | - | - | [8 empty] | O - Marco Serrão
| NEW |  |  |  | 226 | F4_033 | Implement BALANCE Program | T |  | % Program implemented | 100% | [20 empty] | O - Marco Serrão
| Data Office |  | 2023 |  | 227 | F4_034 | Data Literacy Program (ongoing) | T | I | Nº Participations | 2000 | 0 | 0 | 0 | 2000 | - | - | - | - | - | - | - | - | [8 empty] | O - Marco Serrão | [11 empty] | O - Elisabete Fonseca
| Data Office |  | 2023/24 |  | 229 | F4_035 | Data Scientists Upskill & Reskill Program | T | A | Nº Participations | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | - | - | - | - | [8 empty] | O - Marco Serrão | [11 empty] | O - Elisabete Fonseca
Driver #2 |  | Advocate people's wellbeing as top priority | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| People | Y | 2023 | - | 232 | F4_037 | Develop an annual Wellbeing plan in all geographies, including a dedicated week to the topic | T |  | nº events/year | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | [8 empty] | O - Alexandra Pinote
| People | N | 2023 |  | 233 | F4_038 | Define a plan to support People more exposed to potential mental health problems | T |  | % Plan defined | 100% | 0 | 0 | 0 | 100% | - | - | - | - | - | - | - | - | [8 empty] | O - Alexandra Pinote
| People | N | 2023 |  | 234,235,236,237,238,239,240,241 | F4_039 | Implement HESTIA plan in the new HQ (F4): - Promote gym facilities (or discounts in partnerships) or wellbeing rooms in the main Galp's offices - Provide healthy snacks for employees in all geographies (fruit, etc.) - Develop on-site lactation/breast feeding rooms in the main Galp's offices - Implement WELL Platinum New Mother requirement on new headquarters - Provision of dedicated lactation rooms with supportive amenities, as well as paid break times, travel accommodations and resources to help mothers initiate and sustain breastfeeding. - Implement WELL Platinum Physical Activity Spaces and Equipment on new headquarters - Provide access to a physical activity space at no cost through an on-site fitness facility, nearby facility or nearby outdoor spaces, such as a park - Implement WELL Platinum Restorative Spaces requirement on new headquarters - Provide spaces that promote a restorative environment and encourage relief from mental fatigue and stress. - Implement WELL PlatinumThermal Comfort Monitoring requirement on new headquarters - Monitor thermal comfort parameters using sensors in their buildings that can be used as feedback for building managers and users to take appropriate actions. | T |  | nº actions started implemented | X | 0 | 0 | 0 | 7 | - | - | - | - | - | - | - | - | [8 empty] | S - Alexandra Pinote | [7 empty] | O - André Silva

## PROMOTE VAL CONSCIOUS BUSINESS
[10 empty] | TOTAL INITIATIVES | [14 empty] | X*
TOTAL INITIATIVES UPDATED
#Actions 2023
|  | #Actions 2024 | [20 empty] | #Actions Owner
|  | #Actions 2025 | [20 empty] | #Actions Stakeholder
Our ambition |  | Embed sustainability in our culture
| Source | Recurrency (Y/N) | Start Year | End Year | ID old | ID | Initiative | Transversal (T) vs Specific (S) | Incremental (I) vs Additional (A) | KPI | Target | Target 2023 |  |  |  | Target 2024 |  |  |  | Target 2025 |  |  |  | Commercial | Renewables | New Businesses | P&O Upstream | P&O Refinery | P&O ROL | Energy Management | CC HSE | CC People | CC Risk | CC Compliance & Legal | CC CSI & Comms | CC Procurement | CC P&P | CC IR | CC IT | CC Facilities | CC External Relations | Internal Audit | CC Finance | Data Office | Innovation | Account & Tax | S&S | Co-onwer?
Driver #1 |  | Shared accountability for success | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| CSI&Comms | Y | 2023 |  | 242 | F5_001 | Define an internal sustainability communication plan (posters, newsletters,etc) | T | A | Communication plan defined and started to be implemented | Y | 0 | 0 | 0 | Y | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [11 empty] | S- Diogo Sousa | [11 empty] | O - Cláudia Santiago
| CC Finance | N | 2023 |  | 243 | F5_002 | Develop a Sustainability-Linked Financial Framework to support the use of ESG financial products | T | A | Framework defined and started to be implemented | Y | 0 | 0 | 0 | Y | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [19 empty] | O - Funding & Trade Finance |  |  |  | O - Cláudia Santiago
| CC Finance | N | 2023 | 2025 | 244 | F5_003 | Include in the pension funds investment policy and in its follow-up, general principles aligned with best practices and respect for ESG factors | T | A | Policy reviewed and released | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [19 empty] | O - Pensions Funds |  |  |  | S - Cláudia Santiago
| S&S, P&P |  | 2023 |  | 337 | F5_005 | Introduce the implementation of Sustainability Roadmap as a KPI |  |  | KPI implemented | Y | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | Y | Y | [13 empty] | O | [9 empty] | S - Cláudia Santiago
| S&S, P&P |  | 2024 |  | 338 | F5_006 | Introduce the implementation of Sustainability Roadmap as an OKR per BU |  |  | OKR implemented | Y | - | - | - | - | 0 | 0 | 0 | Y | Y | Y | Y | Y | [13 empty] | O | [9 empty] | S - Cláudia Santiago
Our ambition |  | Transparency and ethics as key principles
|  | Recurrency (Y/N) | Start Year | End Year | ID |  | Initiative | Transversal (T) vs Specific (S) | Incremental (I) vs Additional (A) | KPI | Target | Target 2023 1Q: Target 2023; Target 2024 1Q: Target 2024; Target 2025 1Q: Target 2025 | Commercial | Renewables | New Businesses | P&O Upstream | P&O Refinery | P&O ROL | Energy Management | CC HSE | CC People | CC Risk | CC Compliance & Legal | CC CSI & Comms | CC Procurement | CC P&P | CC IR | CC IT | CC Facilities | CC External Relations | Internal Audit | CC Finance | Data Office | Innovation | Account & Tax | S&S
Driver #1 |  | Zero tolerance for unethical practices | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| RM | N | 2023 |  | 253 | F5_011 | Implement a fraud risk management programme, through a governance model and specific regulations (definition of preventive and detective control activities, the process of identification, evaluation, reporting and correction of fraud events in the Galp Group) | T | A | Fraude risk management framework defined and started to be implemented | Y | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | Y | Y | [9 empty] | O - Ana Sofia Silva
| Internal Audit | N | 2023 |  | 254 | F5_012 | Implement a survey to be completed in every audit engagement reated to ethics, compliance, risk management and internal control | T | A | nº Surveys implemented in applicable audits/nº applicable audits | 100% NA - 100% | 0 | 0 | 0 | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | 100% NA - 100% | [18 empty] | O - Laura Carvalho Santos
| NEW | Y | 2024 |  | 255 | F5_013 | Report tax country by country | T | A | Report released | Y | - | - | - | - | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 100% | [22 empty] | O | S - Claudia Santiago
Driver #2 |  | Increment greater ESG disclosure, clarity, and accuracy | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| IT | N | 2023 |  | 259 | F5_020 | Implement a new IT System to report all ESG needed information requested by mandatory and voluntary reporting frameworks (GILC-1086). | T | A | Progress Rate (%) | 100% | 0 | 0 | 0 | 100% | - | - | - | - | - | - | - | - | [15 empty] | O - Nuno valença
| S&S | N | 2023 |  | 260 | F5_022 | Update and publish Climate Policy position | T | A | Policy updated and released | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [23 empty] | O - Cláudia Santiago
|  |  | 2023 |  | 336 | F5_023 | Disclose amounts paid to trade associations and expenditure on lobbying |  |  | nºreports/year | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | [17 empty] | O - Ana Silveira
| S&S | Y | 2023 |  | 262 | F5_024 | Report the eligibility and alignment of our activities in accordance with EU Taxonomy, on an annual basis | T | A | nº reports/year | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | [23 empty] | O - Cláudia Santiago
| ER |  | 2023 |  | 333 | F5_025 | Define a Stakeholder Engagement Policy |  |  | Policy released | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [17 empty] | O - Ana Silveira
| S&S | Y | 2024 |  | 261 | F5_026 | Launch an annual ESG investors' day | T | A | No events/year | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | [14 empty] | O - Teresa Toscano | [8 empty] | S - Cláudia Santiago
Our ambition |  | Sustainable supply chain driving our business
|  | Recurrency (Y/N) | Start Year | End Year | ID |  | Initiative | Transversal (T) vs Specific (S) | Incremental (I) vs Additional (A) | KPI | Target | 1Q: Target 2023; 1Q: Target 2024; 1Q: Target 2025 | Commercial | Renewables | New Businesses | P&O Upstream | P&O Refinery | P&O ROL | Energy Management | CC HSE | CC People | CC Risk | CC Compliance & Legal | CC CSI & Comms | CC Procurement | CC P&P | CC IR | CC IT | CC Facilities | CC External Relations | Internal Audit | CC Finance | Data Office | Innovation | Account & Tax | S&S
Driver #1 |  | ESG as primary criteria for managing all our suppliers | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| RNW | N | 2023 |  | 313 | F5_032 | Include in all tender process Galp' human rights policy and possibility to perform audits (relevant contracts) | S | A | % tender process covered | 100% | [13 empty] | O | [8 empty] | S |  | S | [10 empty] | S - Cláudia Santiago
| Procurement | N | 2023 |  | 272.275 | F5_033 | Review ESG commitments & targets to be incorporated in suppliers evaluation (safety, biodiversity/no deforestation, GHG emission reduction by 2030, carbon footprint, low water impact,human rights, anti-corruption, etc.) | T | I | nº Capacity Building session about standard updated | 1 | - | - | - | - | 0 | 0 | 0 | 1 | - | - | - | - | [12 empty] | O - Mara Pereira | [10 empty] | O
| EM | N | 2024 |  | 305 | F5_029 | Review the process for the qualification, selection and monitoring of business partners, based on ESG criteria, across all BU's | T | I | nº Capacity Building session about standard updated | 1 | 0 | 0 | 0 | 1 | - | - | - | - | - | - | - | - | O | O | O | O | O | O
| EM, Procurement | N | 2024 |  | 270 | F5_028 | Review the process for the qualification, selection and monitoring of suppliers based on ESG criteria, across all BU's | T | I | nº Capacity Building session about standard updated | 1 | 0 | 0 | 0 | 1 | - | - | - | - | - | - | - | - | [6 empty] | S - Sara Montenegro | [5 empty] | O - Mara Pereira | [10 empty] | S - Cláudia Santiago
| Procurement,S&S | Y | 2024 |  | 271 | F5_030 | Assess suppliers in ESG criteria | T |  | % suppliers (tier 1 and non-tier 1) assessed in the last 3 years | 95% | 0% | 0% | 0% | 95% | 0% | 0% | 0% | 95% | 0% | 0% | 0% | 95% | [12 empty] | O - Mara Pereira
Driver #2 |  | Act for change, together with our suppliers | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| RNW |  | 2023 |  | 314 | F5_038 | Evaluate opportunities behind PV Value Chain EU reshoring & recycling (supported by EU institutions) | S | A | Evaluation performed | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - |  |  | S | [18 empty] | O
| Facilities |  | 2024 |  | 280 | F5_039 | Map plastic usage in value chain | S | A | % Mapping performed | 100% | [24 empty] | S - Mara Pereira |  |  | S - IT&D | O - André Miranda da Silva
| Procurement |  | 2024 |  | 281 | F5_040 | Review sustainability procurement policy to include minimum living wages, acceptable living conditions, corporal punishment/disciplinary practice | T | A | Policy reviewed and released | Y | - | - | - | - | 0 | 0 | 0 | Y | - | - | - | - | [12 empty] | O - Mara Pereira | [10 empty] | S
| Procurement |  | 2024 |  | 283 | F5_041 | Promote training and engagement sessions for specific suppliers (in topics such as cybersecurity, safety, human rights, etc.) | T | A | nº sessions performed/nºsessions planned | 100% | - | - | - | - | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | [12 empty] | O - Mara Pereira
| Procurement |  | 2024 |  | 284 | F5_042 | Create a supplier diversity program | T | A | Program created and started to be implemented | Y | - | - | - | - | 0 | 0 | 0 | Y | Y | Y | Y | Y | [12 empty] | O - Mara Pereira | [10 empty] | S
| Procurement |  | 2025 |  | 285 | F5_043 | Implement an annual Suppliers Award, based on ESG performance | T | A | No events/year | 1 | - | - | - | - | - | - | - | - | 0 | 0 | 0 | 1 | [12 empty] | O - Mara Pereira | [10 empty] | S
| Procurement |  | 2025 |  | 286 | F5_044 | Promote periodic meeting sessions with suppliers to improve engagement and awareness in topics such as cybersecurity, safety, human rights, among others | T | A | nº meetings performed/nºmeetings planned | 100% | - | - | - | - | - | - | - | - | 0% | 0% | 0% | 100% | [12 empty] | O - Mara Pereira
Our ambition |  | No significant cyber security breach
|  | Recurrency (Y/N) | Start Year | End Year | ID |  | Initiative | Transversal (T) vs Specific (S) | Incremental (I) vs Additional (A) | KPI | Target | 1Q: Target 2023; 1Q: Target 2024; 1Q: Target 2025 | Commercial | Renewables | New Businesses | P&O Upstream | P&O Refinery | P&O ROL | Energy Management | CC HSE | CC People | CC Risk | CC Compliance & Legal | CC CSI & Comms | CC Procurement | CC P&P | CC IR | CC IT | CC Facilities | CC External Relations | Internal Audit | CC Finance | Data Office | Innovation | Account & Tax | S&S
Driver #1 |  | Strengthen cyber resilience in our operations | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| RM | N | 2023 |  | 288 | F5_045 | Strength collaboration with governments, law enforcement and peers to exchange on new and emerging threats | T | A | Intel Sharing Sources | N/A | [21 empty] | O - Luís Morais
| RM | N | 2024 |  | 287 | F5_046 | Position Galp in the Global Top Quartile in Cyber Resilience Maturity (e.g. Bitsight ratings or Mckinsey benchmark) | S | A | Maturity level | 2.8/4 | [21 empty] | O - Luís Morais
Driver #2 |  | Incorporate Cyber culture in our DNA | [9 empty] | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q
| EM | N | 2023 |  | 294 | F5_049 | Perform a Workshop on Cyber security Specific for EM | S | A | Workshop performed | Y | 0 | 0 | 0 | Y | - | - | - | - | - | - | - | - | [6 empty] | S - Sara Montenegro |  |  | O - Luís Morais | [5 empty] | S - Rui de Oliveira
| RM | N | 2023 |  | 298 | F5_050 | Improve Cyber Awareness and Trainings through adaptive learning and gamification concepts | S | I | % applied workers trained | 100% | 0 | 0 | 0 | 100% | - | - | - | - | - | - | - | - | [9 empty] | O - Luís Morais
| RM | N | 2023 |  | 299 | F5_051 | Define a cyber value-at-risk approach and value assurance unit, to ensure risk-based focus and prioritization of investments and innitiatives | S | A | Cyber value-at-risk approach for Cyber Resilience 2024 Roadmap | Cover all affected Business Units | [21 empty] | O - Luís Morais
| Internal Audit | Y | 2023 |  | 300 | F5_052 | Include in the annual audit plan cybersecurity audit projects, including IT General Controls | S | A | nº audits/year | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | [15 empty] | S |  |  | O - Aboobakar Kara |  | S
| RM | N | 2024 |  | 301 | F5_053 | Inject Cyber-security by design during EPC lifecycle for industrial operations | S | A | Review Architecture and incliude Cybersecurity requirements in EPC for OT | All major P&O and Renewables | [21 empty] | O - Luís Morais